## ProjectSchedule
PROJECT TITLE |  | Replace sample greyed-out data with your own.
[Company Name] |  | Project Start: | 2023-02-01
[Project Lead] |  | Today: | 2024-01-08
|  | Display Week: | 0 |  |  |  | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24
 | time axis 2023-01-23 to 2023-04-30
TASK | ASSIGNED TO | PROGRESS | START | END | WORKDAYS | DAYS | time axis 2023-01-23 to 2023-04-30
FORMULATE PROJECT
Introduction by Project Leader |  | 30% | 2023-02-01 | 2023-02-04 | 3 | 4
Brainstorm project contours |  | 60% | 2023-02-05 | 2023-02-07 | 2 | 3
Build LFS or SE or ToC |  | 50% | 2023-02-08 | 2023-02-12 | 3 | 5
Build Ubuntu Circle |  | 25% | 2023-02-13 | 2023-02-15 | 3 | 3
Qualify prospects |  |  | 2023-02-16 | 2023-02-22 | 5 | 7
BUILD BUDGET
Cost resource checklist |  | 50% | 2023-02-23 | 2023-02-28 | 4 | 6
Conduct forecasting exercise |  | 50% | 2023-03-01 | 2023-03-05 | 3 | 5
Develop 1st Draft budget |  |  | 2023-03-06 | 2023-03-10 | 5 | 5
Finalise Master Budget (multi-year) |  |  | 2023-03-12 | 2023-03-20 | 6 | 9
Distil Summary Budget |  |  | 2023-03-21 | 2023-03-21 | 0 | 1
SOLICITATION DOCUMENTS
Write Concept note |  |  | 2023-03-06 | 2023-03-07 | 2 | 2
Develop Case for Support |  |  | 2023-03-08 | 2023-03-10 | 3 | 3
Write proposal/proposition |  |  | 2023-03-11 | 2023-03-20 | 6 | 10
Write Letter of Enquiry |  |  | 2023-03-20 | 2023-03-22 | 2 | 3
Design appointment schedule |  |  | 2023-03-20 | 2023-03-30 | 8 | 11
CULTIVATION
Schedule contact meetings |  |  | 2023-03-20 | 2023-03-27 | 5 | 8
Make exchange/ASK |  |  | 2023-04-01 | 2023-04-15 | 8 | 15
Scrutinize Agreement |  |  | 2023-04-10 | 2023-04-12 | 2 | 3
Design Action Plans |  |  | 2023-04-12 | 2023-04-15 | 3 | 4
Schedule kick-off / launch |  |  | 2023-04-20 | 2023-04-22 | 2 | 3
STEWARDSHIP Programme
Acknowledgement letter |  |  | 2023-04-13 | 2023-04-14 | 2 | 2
Acknowledgement phone call & newsbrief |  |  | 2023-04-16 | 2023-04-16 | 0 | 1
Blog / Newsletter publicising donation |  |  | 2023-04-18 | 2023-04-20 | 3 | 3
Branded gift |  |  | 2023-04-24 | 2023-04-25 | 2 | 2
Invitation |  |  | 2023-04-30 | 2023-05-01 | 0 | 2
66
Insert new rows ABOVE this one
Replace or delete appropriate dates & holiday names.
Public Holidays (Light Blue)
2023-01-01 | New Year's Day
2023-03-21 | Human Rights Day
2023-04-07 | Good Friday
2023-04-27 | Freedom Day
2023-04-10 | Family Day
2023-05-01 | Workers Day
2023-06-16 | Youth Day
2023-08-09 | Womens' Day
2023-09-25 | Heritage Day
2023-12-16 | Reconciliation
2023-12-25 | Christmas Day
2023-12-26 | Boxing Day
SIMPLE GANTT CHART by Vertex42.com 13/01/2018
Free version has been modified by adding timeline, public holidays, workdays only, & a sample campaign plan https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html © 2018-2019 Vertex42 LLC
Note on BG2: Janine4: chart is very dificult to read
Note on I6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.